ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

BACKGROUND INFORMATION

Partner country

< Albania >

Contracting authority

<NGO Diagnosis>

Country background

Albania struggles with medical workforce shortages, fragmented healthcare infrastructure, geographical barriers and under-equipped rural clinics, leading to delays in care delivery and limitations to quality health services accessibility.

The project responds to these common territorial challenges by addressing healthcare gaps in Dropull Municipality, where there is largely elderly population with chronic conditions and limited mobility, aiming to improve access to healthcare services for the population, particularly in remote areas, increase capacity and capabilities of local health professionals, and support the resilience of the health system by improving the equipment to respond to emergencies.

The initiative includes equitable access to healthcare by upgrading local health facilities with modern telemedicine technology and providing the necessary training to staff. The main outcomes are the implementation of telemedicine platforms in local health centre, the installation of high-resolution examination cameras, vital signs monitors, and other medical equipment. Additionally, training programs for healthcare professionals in telemedicine and emergency medical response will take place as well as the development of a network for continuous medical education and support between central hospitals and rural health centres. The innovation lies in the integration of physical presence and remote healthcare services, adapted to the geographical and demographic needs of the region.

The outputs developed by the project will be integrated into daily operations in local health centres of Municipality of Dropull.

Current situation in the sector

< There are critical healthcare disparities in the cross-border region between Greece and Albania, where rural and remote communities face limited access to medical care and sectoral, infrastructure and geographical barriers lead to delays in urgent care delivery. Therefore, rural areas represent underserved populations with significant healthcare disparities, making them ideal for targeted interventions.

As an organization, NGO Diagnosis supports public awareness, training and healthcare delivery in remote and rural villages. It is dedicated to provide healthcare to vulnerable populations in rural areas in cooperation with relevant municipalities and local legislation.>

Related programmes and other donor activities

< N/A >

OBJECTIVES & EXPECTED OUTPUTS

Overall objective

The overall objective (Impact) to which this action contributes is:

The Project “Enhancing Healthcare Access in Municipality of Dropull through Greece-Albania Cooperation Background’’, with the Acronym “EpirusMedEye”, aims to strengthen the healthcare infrastructure in the Municipality of Dropull by integrating advanced telemedicine systems and providing the necessary medical equipment to local health centres.

The Project will significantly improve access to quality health services and resilience of the health system for the region's remote and rural populations, who are currently underserved due to geographic isolation and an aging demographic profile by upgrading local health facilities with modern telemedicine technology other medical equipment and providing the necessary training to staff.

Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

- Contribution to telemedicine infrastructure development (D3.1)

- Contribution to capacity building and training (D4.1, 4.2).

- Contribution to the pilot implementation and evaluation (D5.2, 5.3).

Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

| Outputs | Title |
| --- | --- |
| 1.2 | Administrative Management Activities – Progress Reports |
| 1.3 | Participation in project meetings |
| 1.4 | Financial Management Activities – Auditing, Financial Reports |
| 2.4 | Video promotion and media presence – Production of promotional material (1 permanent plaque and 50 posters) for informing citizens |
| 3.1 | Contribution to Needs Assessment report for existing Healthcare Facilities |
| 4.1 | Report with the contribution on the development of training materials and resources |
| 4.2 | Report with the contribution on the local workshop and training session lead by the PB1 |
| 5.2 | 20 visits to villages for data collection |
| 5.3 | Support, assistance and feedback collection during the 20 visits |

ASSUMPTIONS & RISKS

Assumptions underlying the project

The main assumptions underlying the project are the following:

- The maturity of the project activities is at satisfactory level. Sufficient capacity of the involved stakeholders and target groups to participate in the project events/activities.

- Existing / Previous data and technical services in general will be available.

- Previous studies including reports, planning activities, financial and economic incentives, methods of analysis of the Health Sector in the Dropull area and at country level will be available.

- The project’s activities will be in line with the needs of the stakeholders involved and political support will facilitate the integration of this in the concerned areas.

Risks

| Risk | Weight | Probability of occurrence | Mitigation measure |
| --- | --- | --- | --- |
| Inability to elaborate the necessary communication means as requested in by the Contract. | High | Low | The contractor is requested to have experience in EU projects. |
| Low capacity of the region and the country to implement the proposed measures-activities. | High | Low | Strong political commitment is in place to meet the sustainable development requirements and impose the necessary measures. |
| Low capacity of the involved stakeholders and target groups to participate in the project activities / events. | Medium | Medium | The invitation approach / the communication channels and the agenda of the events will be redesigned. New dates will be chosen, if necessary, to address the requirements of most stakeholders. |
| Possible delays in project implementation | Medium | Medium | The project timetable will be re-designed, if necessary. A prolongation request will be submitted in case of major delays. |

SCOPE OF THE WORK

General

Description of the assignment

< The scope of the assignment is to provide integrated consulting support to the Contracting Authority for the implementation of the project deliverables listed in section 4.2. >

Geographical area to be covered

< Albania, Dropull Municipality >

Target groups

The project's main target groups are:

- Local communities,

- elderly residents with limited mobility and chronic health conditions

- local healthcare professionals,

- Healthcare institutions:

- policymakers, and

- EU stakeholders in Greece and Albania.

Specific work

LOT 1 – Management and Communication Services

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 1.2 | Administrative Management | Provision of external expertise services providing support with (a) day-to-day project management, including the continuous communication with the LB, data collection, report drafting at regular basis, but also for any other kind of reports or data will be requested by the LB, the preparation of modification requests, and (b) the project financial monitoring, collecting and analysing PBs data but also the preparation of the documentation needed for the administrative FLCs of PB. | Up to 13/10/2027 |
| 1.3 | Technical Management | Provision of external expertise services to participate in project meetings | Up to 13/10/2027 |
| 1.4 | Financial Management | Provision of external expertise services to manage the project finances, including budget tracking, expense monitoring, and financial reporting, to ensure financial sustainability and accountability throughout the project lifecycle. | Up to 13/10/2027 |
| 2.4 | Project's Promotional Material | Provisions of external expertise services for designing, printing and distributing promotional materials for different stakeholders and promoting the project through video and media presence. | Up to 13/10/2027 |

LOT 2 – Technical Activities

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 3.1 | Needs Assessment of Existing Healthcare Facilities | Provision of external expertise services for supporting in validation of findings and adaptation of recommendations for rural health needs. | Up to 13/10/2027 |
| 4.1 | Design and Development of Training Programs for Telemedicine | Provision of external expertise services to support in the development of training materials and resources for rural healthcare providers. | Up to 13/10/2027 |
| 4.2 | Execution of Interactive Workshops and Training Sessions | Provision of external expertise services for supporting the PB01 in coordinating a local workshop and training session in Dropull, and ensures active participation from healthcare providers. | Up to 13/10/2027 |

LOT3 – Pilot Activity (medical visits)

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 5.2 | Continuous Monitoring and Data Collection for Evaluation Purposes | Provisions of external expertise services for collecting data on the performance of the telemedicine services and feedback from healthcare providers and patients. The contractor will conduct 20 visits to the villages for collection of data. Each visit will last 2 days, and one doctor and auxiliary medical staff are to participate at minimum. | Up to 13/10/2027 |
| 5.3 | Feedback Collection from Healthcare Providers and Patients | Provisions of external expertise services for collecting qualitative feedback from healthcare providers and patients on the effectiveness and challenges of telemedicine services. Auxiliary medical personnel, consisted by 3 people (1 Paramedic Ambulance Crew, 1 Microbiological Medical Laboratory Technologist and 1 Medical Laboratory/Radiology Technologist) will assist the medical team during the visits and will provide general support to the medical team. | Up to 13/10/2027 |

Project management

Responsible body

NGO Diagnosis, non-governmental organization located in Gjirokaster, Albania.

Management structure

NGO diagnosis is a non-governmental organization based in Girokaster and has experience in serving vulnerable populations, supporting public engagement, healthcare delivery, and training to improve medical services. It operates in the healthcare sector and in the past had been focused on aiding the elderly residents of specific remote areas in Albania in cooperation with the relevant municipalities.

Facilities to be provided by the contracting authority and/or other parties

< N/A >

LOGISTICS AND TIMING

Location

Albania / Dropull Municipality

Start date & period of implementation of tasks

The intended start date is <14/09/2026> and the period of implementation of the contract will be <13> months from this date. Please see point 3 of the main conditions for the actual start date and period of implementation.

REQUIREMENTS

Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover, proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

[The Organisation & Methodology must include a paragraph demonstrating that a gender sensitive experts’ selection procedure has been applied]

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

Experts

Key experts are not required

The Organisation and Methodology should demonstrate how the contract will comply with these requirements to accomplish the desired output(s). The Organisation and Methodology may include the name of an expert and his profile. Compliance (yes/no answer) of the team (as a whole) with the requirements will be checked, but there will be no marks given to the experts.

Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by [the contractor].

Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

REPORTS

Reporting requirements

The contractor will submit the following reports in <English> in one original and one copy:

- Inception Report of maximum 12 pages to be produced after one month from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

Draft final report of maximum <15> pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on Minority Inclusive Medical Outreach for Remote Mountainous Areas. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

MONITORING AND EVALUATION

Definition of indicators

< No special requirements are envisaged >

Special requirements

< No special requirements are envisaged>

* * *

Note that gender balance refers not only to numerical parity, but also to the level of employment and remuneration, roles and functions.